## Projects
Project_ID | Project_Name | Sponsor | Project_Manager | Start_Date | End_Date | Budget_kEUR | Status | RAG_Status | Portfolio
PRJ001 | CRM Rollout | Head of Operations | PM_1 | 2024-03-23 | 2024-06-29 | 480 | On Track | Red | Customer Experience
PRJ002 | Intranet Redesign | COO | PM_2 | 2024-04-03 | 2024-10-29 | 400 | At Risk | Red | Customer Experience
PRJ003 | Cloud Migration Wave 1 | COO | PM_3 | 2024-04-21 | 2024-10-05 | 220 | On Track | Green | Infrastructure
PRJ004 | Data Governance Implementation | COO | PM_4 | 2024-01-16 | 2024-08-07 | 220 | On Track | Green | Infrastructure
PRJ005 | Security Hardening Phase 2 | COO | PM_5 | 2024-01-13 | 2024-05-08 | 420 | At Risk | Amber | Infrastructure
PRJ006 | Customer Portal Upgrade | COO | PM_6 | 2024-02-06 | 2024-08-22 | 440 | Delayed | Green | Core Systems
PRJ007 | Mobile App Enhancement | Head of Sales | PM_7 | 2024-01-27 | 2024-08-22 | 480 | At Risk | Amber | Customer Experience
PRJ008 | Analytics Platform Pilot | Head of Sales | PM_8 | 2024-05-20 | 2024-08-04 | 100 | At Risk | Amber | Infrastructure
PRJ009 | HR System Integration | Head of Sales | PM_9 | 2024-03-21 | 2024-09-16 | 360 | Delayed | Amber | Core Systems
PRJ010 | Network Modernisation | CIO | PM_10 | 2024-02-16 | 2024-10-11 | 120 | Delayed | Green | Infrastructure
PRJ011 | Website Relaunch | CFO | PM_11 | 2024-03-28 | 2024-09-18 | 460 | On Track | Red | Infrastructure
PRJ012 | Finance Automation | CIO | PM_12 | 2024-02-12 | 2024-07-08 | 380 | Complete | Red | Customer Experience
PRJ013 | Service Desk Transformation | CFO | PM_13 | 2024-05-22 | 2024-12-14 | 280 | Delayed | Green | Infrastructure
PRJ014 | Vendor Onboarding Streamline | COO | PM_14 | 2024-05-28 | 2024-11-20 | 120 | Delayed | Amber | Customer Experience
PRJ015 | Document Management Upgrade | CFO | PM_15 | 2024-01-16 | 2024-09-11 | 480 | Complete | Amber | Infrastructure

## Milestones
Milestone_ID | Project_ID | Milestone_Name | Planned_Date | Actual_Date | Owner | Status
MS_PRJ001_1 | PRJ001 | Testing Complete | 2024-04-06 | 2024-03-27 | Lead_6 | Delayed
MS_PRJ001_2 | PRJ001 | Go/No-Go | 2024-04-20 | 2024-04-29 | Lead_2 | Not Started
MS_PRJ001_3 | PRJ001 | Build Complete | 2024-05-04 | 2024-04-30 | Lead_8 | Completed
MS_PRJ001_4 | PRJ001 | Go/No-Go | 2024-05-18 | 2024-05-20 | Lead_3 | Delayed
MS_PRJ001_5 | PRJ001 | Go/No-Go | 2024-06-01 | 2024-05-27 | Lead_18 | Delayed
MS_PRJ001_6 | PRJ001 | Go/No-Go | 2024-06-15 | 2024-06-13 | Lead_18 | In Progress
MS_PRJ002_1 | PRJ002 | Testing Complete | 2024-05-02 | 2024-05-14 | Lead_13 | Delayed
MS_PRJ002_2 | PRJ002 | Design Complete | 2024-06-01 | 2024-05-29 | Lead_6 | In Progress
MS_PRJ002_3 | PRJ002 | Handover to BAU | 2024-07-01 | 2024-06-25 | Lead_8 | In Progress
MS_PRJ002_4 | PRJ002 | Go-Live | 2024-07-31 | 2024-07-21 | Lead_6 | Delayed
MS_PRJ002_5 | PRJ002 | Design Complete | 2024-08-30 | 2024-08-28 | Lead_5 | Completed
MS_PRJ002_6 | PRJ002 | Go-Live | 2024-09-29 | 2024-10-02 | Lead_19 | Completed
MS_PRJ003_1 | PRJ003 | Go/No-Go | 2024-05-14 | 2024-05-08 | Lead_18 | Not Started
MS_PRJ003_2 | PRJ003 | Go/No-Go | 2024-06-07 | 2024-06-09 | Lead_13 | Delayed
MS_PRJ003_3 | PRJ003 | Handover to BAU | 2024-07-01 | 2024-06-24 | Lead_13 | Delayed
MS_PRJ003_4 | PRJ003 | Design Complete | 2024-07-25 | 2024-07-16 | Lead_7 | In Progress
MS_PRJ003_5 | PRJ003 | Design Complete | 2024-08-18 | 2024-08-22 | Lead_11 | In Progress
MS_PRJ003_6 | PRJ003 | Design Complete | 2024-09-11 | 2024-09-20 | Lead_1 | Not Started
MS_PRJ004_1 | PRJ004 | Testing Complete | 2024-02-07 | 2024-02-01 | Lead_20 | Not Started
MS_PRJ004_2 | PRJ004 | Build Complete | 2024-03-01 | 2024-02-20 | Lead_20 | Not Started
MS_PRJ004_3 | PRJ004 | Handover to BAU | 2024-03-24 | 2024-03-26 | Lead_9 | In Progress
MS_PRJ004_4 | PRJ004 | Go/No-Go | 2024-04-15 | 2024-04-16 | Lead_4 | Completed
MS_PRJ004_5 | PRJ004 | Go/No-Go | 2024-05-08 | 2024-05-01 | Lead_16 | Delayed
MS_PRJ004_6 | PRJ004 | Design Complete | 2024-05-31 | 2024-06-05 | Lead_5 | Completed
MS_PRJ004_7 | PRJ004 | Handover to BAU | 2024-06-22 | 2024-06-15 | Lead_9 | Completed
MS_PRJ004_8 | PRJ004 | Go-Live | 2024-07-15 | 2024-07-20 | Lead_1 | In Progress
MS_PRJ005_1 | PRJ005 | Build Complete | 2024-02-01 | 2024-02-07 | Lead_18 | Completed
MS_PRJ005_2 | PRJ005 | Handover to BAU | 2024-02-20 | 2024-02-10 | Lead_3 | Completed
MS_PRJ005_3 | PRJ005 | Go-Live | 2024-03-11 | 2024-03-23 | Lead_12 | Completed
MS_PRJ005_4 | PRJ005 | Build Complete | 2024-03-30 | 2024-03-25 | Lead_18 | Completed
MS_PRJ005_5 | PRJ005 | Handover to BAU | 2024-04-18 | 2024-04-25 | Lead_8 | Completed
MS_PRJ006_1 | PRJ006 | Build Complete | 2024-02-28 | 2024-03-14 | Lead_13 | In Progress
MS_PRJ006_2 | PRJ006 | Build Complete | 2024-03-21 | 2024-04-03 | Lead_17 | In Progress
MS_PRJ006_3 | PRJ006 | Handover to BAU | 2024-04-12 | 2024-04-17 | Lead_1 | Completed
MS_PRJ006_4 | PRJ006 | Go/No-Go | 2024-05-04 | 2024-04-24 | Lead_9 | Completed
MS_PRJ006_5 | PRJ006 | Go/No-Go | 2024-05-26 | 2024-05-22 | Lead_12 | Completed
MS_PRJ006_6 | PRJ006 | Build Complete | 2024-06-17 | 2024-06-18 | Lead_4 | Not Started
MS_PRJ006_7 | PRJ006 | Build Complete | 2024-07-09 | 2024-07-06 | Lead_11 | Delayed
MS_PRJ006_8 | PRJ006 | Go-Live | 2024-07-31 | 2024-07-27 | Lead_20 | Delayed
MS_PRJ007_1 | PRJ007 | Handover to BAU | 2024-03-08 | 2024-03-13 | Lead_3 | Completed
MS_PRJ007_2 | PRJ007 | Go/No-Go | 2024-04-19 | 2024-04-30 | Lead_7 | Not Started
MS_PRJ007_3 | PRJ007 | Go/No-Go | 2024-05-30 | 2024-06-04 | Lead_11 | In Progress
MS_PRJ007_4 | PRJ007 | Go/No-Go | 2024-07-11 | 2024-07-03 | Lead_13 | Delayed
MS_PRJ008_1 | PRJ008 | Build Complete | 2024-06-04 | 2024-06-17 | Lead_5 | In Progress
MS_PRJ008_2 | PRJ008 | Go-Live | 2024-06-19 | 2024-06-09 | Lead_15 | In Progress
MS_PRJ008_3 | PRJ008 | Go-Live | 2024-07-04 | 2024-07-19 | Lead_20 | In Progress
MS_PRJ008_4 | PRJ008 | Build Complete | 2024-07-19 | 2024-07-24 | Lead_18 | Completed
MS_PRJ009_1 | PRJ009 | Design Complete | 2024-04-09 | 2024-04-03 | Lead_4 | Not Started
MS_PRJ009_2 | PRJ009 | Go/No-Go | 2024-04-29 | 2024-05-05 | Lead_7 | In Progress
MS_PRJ009_3 | PRJ009 | Testing Complete | 2024-05-19 | 2024-05-15 | Lead_7 | Not Started
MS_PRJ009_4 | PRJ009 | Go-Live | 2024-06-08 | 2024-06-07 | Lead_11 | In Progress
MS_PRJ009_5 | PRJ009 | Build Complete | 2024-06-28 | 2024-06-26 | Lead_2 | Delayed
MS_PRJ009_6 | PRJ009 | Go/No-Go | 2024-07-18 | 2024-07-31 | Lead_19 | Completed
MS_PRJ009_7 | PRJ009 | Go-Live | 2024-08-07 | 2024-08-13 | Lead_5 | Delayed
MS_PRJ009_8 | PRJ009 | Go-Live | 2024-08-27 | 2024-09-03 | Lead_17 | In Progress
MS_PRJ010_1 | PRJ010 | Go-Live | 2024-04-03 | 2024-04-07 | Lead_1 | In Progress
MS_PRJ010_2 | PRJ010 | Build Complete | 2024-05-21 | 2024-06-04 | Lead_5 | In Progress
MS_PRJ010_3 | PRJ010 | Go-Live | 2024-07-07 | 2024-07-12 | Lead_2 | Not Started
MS_PRJ010_4 | PRJ010 | Design Complete | 2024-08-24 | 2024-08-24 | Lead_18 | Delayed
MS_PRJ011_1 | PRJ011 | Testing Complete | 2024-05-01 | 2024-04-28 | Lead_2 | In Progress
MS_PRJ011_2 | PRJ011 | Go-Live | 2024-06-05 | 2024-06-19 | Lead_15 | Not Started
MS_PRJ011_3 | PRJ011 | Design Complete | 2024-07-10 | 2024-07-17 | Lead_15 | Not Started
MS_PRJ011_4 | PRJ011 | Handover to BAU | 2024-08-14 | 2024-08-14 | Lead_9 | In Progress
MS_PRJ012_1 | PRJ012 | Go-Live | 2024-03-01 | 2024-03-07 | Lead_8 | Delayed
MS_PRJ012_2 | PRJ012 | Go-Live | 2024-03-19 | 2024-03-31 | Lead_7 | Completed
MS_PRJ012_3 | PRJ012 | Go/No-Go | 2024-04-07 | 2024-04-11 | Lead_4 | In Progress
MS_PRJ012_4 | PRJ012 | Testing Complete | 2024-04-25 | 2024-04-27 | Lead_3 | Delayed
MS_PRJ012_5 | PRJ012 | Go/No-Go | 2024-05-13 | 2024-05-24 | Lead_3 | In Progress
MS_PRJ012_6 | PRJ012 | Design Complete | 2024-06-01 | 2024-05-28 | Lead_5 | Completed
MS_PRJ012_7 | PRJ012 | Build Complete | 2024-06-19 | 2024-07-01 | Lead_9 | Completed
MS_PRJ013_1 | PRJ013 | Handover to BAU | 2024-06-25 | 2024-06-29 | Lead_4 | In Progress
MS_PRJ013_2 | PRJ013 | Build Complete | 2024-07-29 | 2024-07-31 | Lead_8 | Delayed
MS_PRJ013_3 | PRJ013 | Go-Live | 2024-09-02 | 2024-08-28 | Lead_13 | Delayed
MS_PRJ013_4 | PRJ013 | Build Complete | 2024-10-06 | 2024-10-06 | Lead_12 | Delayed
MS_PRJ013_5 | PRJ013 | Handover to BAU | 2024-11-09 | 2024-11-09 | Lead_12 | Not Started
MS_PRJ014_1 | PRJ014 | Go/No-Go | 2024-07-02 | 2024-07-02 | Lead_1 | Delayed
MS_PRJ014_2 | PRJ014 | Go-Live | 2024-08-06 | 2024-08-08 | Lead_20 | Completed
MS_PRJ014_3 | PRJ014 | Design Complete | 2024-09-10 | 2024-09-09 | Lead_8 | Not Started
MS_PRJ014_4 | PRJ014 | Testing Complete | 2024-10-15 | 2024-10-08 | Lead_9 | Not Started
MS_PRJ015_1 | PRJ015 | Testing Complete | 2024-03-03 | 2024-03-17 | Lead_5 | In Progress
MS_PRJ015_2 | PRJ015 | Go/No-Go | 2024-04-20 | 2024-04-23 | Lead_5 | Completed
MS_PRJ015_3 | PRJ015 | Handover to BAU | 2024-06-07 | 2024-06-14 | Lead_11 | Delayed
MS_PRJ015_4 | PRJ015 | Design Complete | 2024-07-25 | 2024-07-17 | Lead_6 | Completed

## Risks
Risk_ID | Project_ID | Risk_Title | Severity | Impact | Status | Owner | Identified_Date
RISK001 | PRJ007 | Risk_1 | Low | Medium | Open | Owner_11 | 2024-02-01
RISK002 | PRJ013 | Risk_2 | Medium | Low | Closed | Owner_14 | 2024-06-05
RISK003 | PRJ002 | Risk_3 | Medium | Low | Mitigated | Owner_1 | 2024-04-24
RISK004 | PRJ009 | Risk_4 | Medium | Medium | Closed | Owner_3 | 2024-03-23
RISK005 | PRJ009 | Risk_5 | High | Low | Open | Owner_3 | 2024-04-06
RISK006 | PRJ001 | Risk_6 | Low | Low | Mitigated | Owner_11 | 2024-04-11
RISK007 | PRJ009 | Risk_7 | Low | Medium | Mitigated | Owner_9 | 2024-05-03
RISK008 | PRJ003 | Risk_8 | Medium | Medium | Open | Owner_5 | 2024-04-23
RISK009 | PRJ001 | Risk_9 | Low | High | Closed | Owner_9 | 2024-04-04
RISK010 | PRJ009 | Risk_10 | Medium | Low | Mitigated | Owner_2 | 2024-05-02
RISK011 | PRJ014 | Risk_11 | High | Medium | Closed | Owner_8 | 2024-07-01
RISK012 | PRJ014 | Risk_12 | Medium | High | Mitigated | Owner_12 | 2024-06-10
RISK013 | PRJ004 | Risk_13 | Medium | Low | Closed | Owner_12 | 2024-02-25
RISK014 | PRJ003 | Risk_14 | Medium | Medium | Open | Owner_14 | 2024-04-29
RISK015 | PRJ001 | Risk_15 | Low | High | Closed | Owner_15 | 2024-04-08
RISK016 | PRJ007 | Risk_16 | Low | Low | Open | Owner_11 | 2024-03-20
RISK017 | PRJ007 | Risk_17 | High | High | Mitigated | Owner_10 | 2024-02-11
RISK018 | PRJ012 | Risk_18 | Medium | Low | Mitigated | Owner_3 | 2024-02-22
RISK019 | PRJ005 | Risk_19 | Medium | Low | Mitigated | Owner_6 | 2024-02-03
RISK020 | PRJ009 | Risk_20 | Medium | Low | Open | Owner_15 | 2024-04-09
RISK021 | PRJ004 | Risk_21 | Medium | Low | Open | Owner_6 | 2024-02-09
RISK022 | PRJ002 | Risk_22 | Medium | Medium | Closed | Owner_11 | 2024-04-15
RISK023 | PRJ004 | Risk_23 | High | Low | Open | Owner_5 | 2024-03-08
RISK024 | PRJ002 | Risk_24 | Low | Medium | Closed | Owner_1 | 2024-04-28
RISK025 | PRJ001 | Risk_25 | Medium | Medium | Closed | Owner_4 | 2024-03-28
RISK026 | PRJ010 | Risk_26 | High | Low | Closed | Owner_15 | 2024-04-01
RISK027 | PRJ013 | Risk_27 | High | Medium | Mitigated | Owner_12 | 2024-06-22
RISK028 | PRJ003 | Risk_28 | Medium | High | Closed | Owner_11 | 2024-04-30
RISK029 | PRJ001 | Risk_29 | High | High | Closed | Owner_7 | 2024-05-08
RISK030 | PRJ012 | Risk_30 | High | Low | Closed | Owner_13 | 2024-03-15
RISK031 | PRJ010 | Risk_31 | Low | High | Closed | Owner_13 | 2024-04-13
RISK032 | PRJ012 | Risk_32 | High | High | Closed | Owner_4 | 2024-02-17
RISK033 | PRJ001 | Risk_33 | Low | Low | Closed | Owner_6 | 2024-03-29
RISK034 | PRJ007 | Risk_34 | Medium | High | Open | Owner_11 | 2024-01-28
RISK035 | PRJ011 | Risk_35 | High | High | Open | Owner_8 | 2024-04-13
RISK036 | PRJ001 | Risk_36 | Medium | Low | Closed | Owner_15 | 2024-04-24
RISK037 | PRJ015 | Risk_37 | High | Low | Closed | Owner_9 | 2024-01-20
RISK038 | PRJ012 | Risk_38 | High | Medium | Mitigated | Owner_13 | 2024-02-16
RISK039 | PRJ014 | Risk_39 | Medium | Low | Closed | Owner_13 | 2024-06-10
RISK040 | PRJ004 | Risk_40 | High | High | Mitigated | Owner_8 | 2024-03-10

## Issues
Issue_ID | Project_ID | Issue_Title | Severity | Status | Owner | Raised_Date | Resolved_Date
ISS001 | PRJ007 | Issue_1 | High | Open | Owner_10 | 2024-02-05 | 2024-03-06
ISS002 | PRJ004 | Issue_2 | Medium | Resolved | Owner_5 | 2024-01-25 | 2024-03-03
ISS003 | PRJ012 | Issue_3 | Medium | Open | Owner_8 | 2024-03-21 | 2024-04-29
ISS004 | PRJ005 | Issue_4 | Medium | Closed | Owner_5 | 2024-04-08
ISS005 | PRJ005 | Issue_5 | Critical | Open | Owner_15 | 2024-03-12 | 2024-04-10
ISS006 | PRJ005 | Issue_6 | Low | Resolved | Owner_8 | 2024-01-23 | 2024-02-22
ISS007 | PRJ009 | Issue_7 | Critical | In Progress | Owner_15 | 2024-05-17
ISS008 | PRJ004 | Issue_8 | Low | In Progress | Owner_12 | 2024-01-25 | 2024-03-02
ISS009 | PRJ006 | Issue_9 | High | Open | Owner_12 | 2024-02-22 | 2024-03-31
ISS010 | PRJ008 | Issue_10 | Critical | Open | Owner_3 | 2024-09-11 | 2024-10-12
ISS011 | PRJ008 | Issue_11 | Critical | Resolved | Owner_12 | 2024-08-15 | 2024-09-12
ISS012 | PRJ006 | Issue_12 | Low | Resolved | Owner_1 | 2024-03-25 | 2024-04-14
ISS013 | PRJ006 | Issue_13 | Low | In Progress | Owner_12 | 2024-05-23 | 2024-06-17
ISS014 | PRJ012 | Issue_14 | High | Open | Owner_7 | 2024-03-20 | 2024-04-05
ISS015 | PRJ014 | Issue_15 | High | Closed | Owner_13 | 2024-08-11 | 2024-08-15
ISS016 | PRJ001 | Issue_16 | Low | Resolved | Owner_11 | 2024-04-27
ISS017 | PRJ004 | Issue_17 | High | In Progress | Owner_13 | 2024-02-19 | 2024-03-17
ISS018 | PRJ007 | Issue_18 | Critical | In Progress | Owner_12 | 2024-05-19 | 2024-05-20
ISS019 | PRJ015 | Issue_19 | Critical | In Progress | Owner_11 | 2024-04-18
ISS020 | PRJ008 | Issue_20 | Medium | In Progress | Owner_8 | 2024-05-26 | 2024-06-30
ISS021 | PRJ005 | Issue_21 | High | Closed | Owner_11 | 2024-02-20 | 2024-03-07
ISS022 | PRJ008 | Issue_22 | Low | In Progress | Owner_11 | 2024-07-30 | 2024-08-24
ISS023 | PRJ004 | Issue_23 | Medium | Closed | Owner_15 | 2024-03-20 | 2024-04-20
ISS024 | PRJ013 | Issue_24 | Medium | In Progress | Owner_4 | 2024-07-18 | 2024-08-14
ISS025 | PRJ006 | Issue_25 | High | In Progress | Owner_6 | 2024-04-17 | 2024-04-22
ISS026 | PRJ010 | Issue_26 | Critical | Closed | Owner_7 | 2024-03-12
ISS027 | PRJ004 | Issue_27 | High | Open | Owner_8 | 2024-03-04 | 2024-03-21
ISS028 | PRJ006 | Issue_28 | Medium | Open | Owner_5 | 2024-02-22
ISS029 | PRJ007 | Issue_29 | Critical | Resolved | Owner_14 | 2024-03-18
ISS030 | PRJ001 | Issue_30 | Critical | Closed | Owner_10 | 2024-04-08 | 2024-04-10
ISS031 | PRJ002 | Issue_31 | Critical | Closed | Owner_4 | 2024-05-23
ISS032 | PRJ004 | Issue_32 | Low | Closed | Owner_2 | 2024-02-04 | 2024-02-13
ISS033 | PRJ001 | Issue_33 | Medium | Open | Owner_11 | 2024-03-23
ISS034 | PRJ003 | Issue_34 | Critical | Open | Owner_2 | 2024-07-10 | 2024-07-26
ISS035 | PRJ009 | Issue_35 | Medium | Closed | Owner_5 | 2024-07-19 | 2024-08-25
ISS036 | PRJ010 | Issue_36 | High | Closed | Owner_5 | 2024-02-16
ISS037 | PRJ011 | Issue_37 | Critical | In Progress | Owner_9 | 2024-07-13 | 2024-07-28
ISS038 | PRJ007 | Issue_38 | Low | Open | Owner_4 | 2024-04-26 | 2024-05-15
ISS039 | PRJ011 | Issue_39 | Low | Resolved | Owner_4 | 2024-06-18 | 2024-07-14
ISS040 | PRJ015 | Issue_40 | Critical | Open | Owner_12 | 2024-03-03 | 2024-03-17